## DASHBOARD
T3010DW - ISSUES DASHBOARD
TOTAL DE ISSUES
ABERTOS
EM ANÁLISE
RESOLVIDOS
TAXA RESOLUÇÃO (%)

## ISSUES
ID | Prioridade | Tipo | Categoria | Sumário | Status | Data Aberta | Responsável | Versão Reportada | Versão Fix | Raiz | Teste Validação | Comentário Marlus | Comentário ODM | Comentário Ztech | Data Fechamento | OK/NOK Final
29814 | Normal | SW | CAMERA | [T3010W] [AND16] [CAMERA] Missed information camera settings | ABERTO | 2026-05-22 | VictorMiguel | T3010DW.URBR2026051901U.pro.u_pk_s_v0 | [7 empty] | NOK
29813 | High | SW | CAMERA | [T3010W] [AND16] [CAMERA] Dark stripes on front and rear camera | ABERTO | 2026-05-22 | VictorMiguel | T3010DW.URBR2026051901U.pro.u_pk_s_v0 | [7 empty] | NOK
29816 | High | HW | HW VERIFICATION | [T3010W] [AND16] [HW VERIFICATION] Performance | ABERTO | 2026-05-25 | marlusmello | T3010DW.URBR2026051901U.pro.u_pk_s_v0 | [7 empty] | NOK
29817 | Urgent | HW | HW VERIFICATION | [T3010W] [AND16] [HW VERIFICATION] LCD | ABERTO | 2026-05-25 | marlusmello | T3010DW.URBR2026051901U.pro.u_pk_s_v0 | [7 empty] | NOK
29820 | immediate | SW | SW VERIFICATION | [T3010W] [AND16] [SW VERIFICATION] AwLog presents continuous failures when processing log code with special operators in T3010DW | ABERTO | 2026-05-25 | marlusmello | T3010DW.URBR2026051901U.pro.u_pk_s_v0 | [7 empty] | NOK
29821 | urgent | SW | SW VERIFICATION | [T3010W] [AND16] [SW VERIFICATION] Device not recognized on computer in T3010DW | ABERTO | 2026-05-25 | marlusmello | T3010DW.URBR2026051901U.pro.u_pk_s_v0 | [7 empty] | NOK
29829 | High | SW | SW VERIFICATION | [T3010W] [AND16] [SW VERIFICATION] Virtual keyboard does not render in full screen - split layout in T3010DW | RESOLVIDO | 2026-05-25 | marlusmello | T3010DW.URBR2026051901U.pro.u_pk_s_v0 | T3010DW.URBR2026060101U.pro.u_pk_s_v0 | [5 empty] | 2026-05-25 | OK
29830 | High | SW | SW VERIFICATION | [T3010W] [AND16] [SW VERIFICATION] Initial setup screen displays incorrect message "computer" instead of "tablet" | RESOLVIDO | 2026-05-25 | marlusmello | T3010DW.URBR2026051901U.pro.u_pk_s_v0 | T3010DW.URBR2026060101U.pro.u_pk_s_v0 | [5 empty] | 2026-05-25 | OK
29875 | normal | SW | SW VERIFICATION | [T3010W] [AND16] [SW VERIFICATION] Auto-brightness disabled by default on factory settings | ABERTO | 2026-06-01 | marlusmello | T3010DW.URBR2026060101U.pro.u_pk_s_v0 | [7 empty] | NOK
29874 | normal | SW | SW VERIFICATION | [T3010W] [AND16] [SW VERIFICATION] Auto-rotation disabled by default on factory settings | ABERTO | 2026-06-01 | marlusmello | T3010DW.URBR2026060101U.pro.u_pk_s_v0 | [7 empty] | NOK
29822 | low | SW | OTHER | [T3010DW][AND 16][Exploratory] Dock remains visible in Camera app instead of full-screen mode | ABERTO | 2026-05-25 | VictorMiguel | T3010DW.OPEN.URBR_2026051901 | [7 empty] | NOK
29823 | High | SW | OTHER | T3010DW][AND 16][Exploratory] The camera app settings are not translated correctly. | ABERTO | 2026-05-25 | VictorMiguel | T3010DW.OPEN.URBR_2026051901 | [7 empty] | NOK
29824 | low | SW | OTHER | [T3010DW][AND 16][Exploratory] Adding Shortcuts to the Lock Screen | ABERTO | 2026-05-25 | VictorMiguel | T3010DW.OPEN.URBR_2026051901 | [7 empty] | NOK
29825 | High | SW | OTHER | [T3010DW][AND 16][Exploratory] Error changing camera zoom. | RESOLVIDO | 2026-05-25 | VictorMiguel | T3010DW.OPEN.URBR_2026051901 | T3010DW.URBR2026060101U.pro.u_pk_s_v0 | [5 empty] | 2026-05-25 | OK
29826 | normal | SW | OTHER | [T3010DW][AND 16][Exploratory] Incorrect date format in watermark (YYYY-MM-DD instead of DD-MM-YYYY) | ABERTO | 2026-05-25 | VictorMiguel | T3010DW.OPEN.URBR_2026051901 | [7 empty] | NOK
29834 | normal | SW | HW VERIFICATION | T3010W] [AND16] [HW VERIFICATION] Bluetooth exhibits connection loss at short distances (<5m) | ABERTO | 2026-05-26 | inaciobrazil | T3010DW.OPEN.URBR_2026051901 | [7 empty] | NOK
29833 | normal | SW | HW VERIFICATION | [T3010W] [AND16] [HW VERIFICATION] Wi-Fi Download Throughput Significantly Lower Than Reference Device | ABERTO | 2026-05-26 | inaciobrazil | T3010DW.OPEN.URBR_2026051901 | [7 empty] | NOK
29849 | normal | SW | OTHER | [T3010DW] [AND16] [SENSOR] Residual accelerometer drift displayed while device is stationary | ABERTO | 2026-05-28 | GuilhermeLima | T3010DW.OPEN.URBR_2026051901 | [7 empty] | NOK
29850 | High | SW | OTHER | [T3010DW] [AND16] [UI] Rotation suggestion button is not displayed when Auto-rotate is disabled | ABERTO | 2026-05-28 | GuilhermeLima | T3010DW.OPEN.URBR_2026051901 | [7 empty] | NOK
29851 | immediate | SW | OTHER | [T3010DW] [AND16] [SENSOR] Residual gyroscope movement displayed while device is stationary | ABERTO | 2026-05-28 | GuilhermeLima | T3010DW.OPEN.URBR_2026051901 | [7 empty] | NOK
29852 | High | SW | OTHER | [T3010DW] [AND16] [SENSOR] Residual X-axis tilt displayed in Bubble Level app while device is resting flat | ABERTO | 2026-05-28 | GuilhermeLima | T3010DW.OPEN.URBR_2026051901 | [7 empty] | NOK
29853 | High | SW | OTHER | [T3010DW] [AND16] [SENSOR] Residual Y-axis values observed in CPU-Z sensors while device is stationary | ABERTO | 2026-05-28 | GuilhermeLima | T3010DW.OPEN.URBR_2026051901 | [7 empty] | NOK
29879 | normal | SW | SW VERIFICATION | [T3010W] [AND16] [SW VERIFICATION] YouTube Music lock screen widget misaligned to top-left corner | ABERTO | 2026-06-01 | marlusmello | T3010DW.URBR2026060101U.pro.u_pk_s_v0 | [7 empty] | NOK
29880 | urgent | SW | SW VERIFICATION | [T3010W] [AND16] [SW VERIFICATION] Folder icons rendered with low quality and pixelation | ABERTO | 2026-06-01 | marlusmello | T3010DW.URBR2026060101U.pro.u_pk_s_v0 | [7 empty] | NOK
29814 | Normal | SW | CAMERA | [T3010W] [AND16] [CAMERA] Missed information camera settings | ABERTO | 2026-05-22 | VictorMiguel | T3010DW.URBR2026051901U.pro.u_pk_s_v0

## LEGENDA
DEFINIÇÃO DE STATUS
ABERTO | Issue novo, sem ação iniciada
EM ANÁLISE | Marlus/ODM investigando a causa
EM DESENVOLVIMENTO | ODM/Ztech trabalhando na correção
AGUARDANDO VALIDAÇÃO | Fix pronto, aguardando teste
RESOLVIDO | Versão lançada com correção
REJEITADO | Não será corrigido (especificar motivo nos comentários)
CANCELADO | Duplicado ou não aplicável
RESPONSÁVEIS
Marlus | QA/Focal - Validação e rastreamento
marlusmello | QA/Focal - Validação e rastreamento
VictorMiguel | Equipe de testes
GuilhermeLima | Equipe de testes
inaciobrazil | Equipe de testes
ODM | Fornecedor/Desenvolvedor (genérico)
Ztech | Ztech (genérico)